## Dashboard
BioSkinRepair.com — Master Project Plan
Last updated: March 28, 2026 ¦ Domain: bioskinrepair.com ¦ Platform: Vercel ¦ Status: Active
PROJECT SNAPSHOT
Pages Live | Articles Live | Month 1 Complete | Months Remaining | Ahrefs Score | Open Issues
28 | 14 | 7/7 | 5 | 77 | 135
Total HTML pages deployed to Vercel | Cluster articles published (Month 0 + Month 1) | April cluster — all articles live | May through September content clusters | Health score — target: 90+ by Month 3 | 11 errors + 29 warnings + 95 notices
6-MONTH CONTENT ROADMAP
Month | Period | Articles | Category Focus | Milestone | Status | Revenue Focus
Month 0 | Pre-launch (Mar) | 7 | Core conditions + 6 reviews | Site launched + review cluster live | Done | Affiliate links setup
Month 1 | April 2026 | 7 | Barrier Recovery, Ingredients, Glossary | First cluster live — 7 articles | Live | Amazon Associates application
Month 2 | May 2026 | 7 | Ingredient Science, Skin Conditions, Buying Guide | Hyaluronic acid, fungal acne, best ceramide | Planned | First affiliate clicks
Month 3 | June 2026 | 7 | Routines, Comparisons, Reviews | Retinol reintro, cleanser guide | Planned | $200 affiliate target
Month 4 | July 2026 | 7 | Ingredient Science, Buying Guides, Reviews | Peptides, best SPF sensitive, Aveeno vs CeraVe | Planned | $500 affiliate target
Month 5 | August 2026 | 7 | Routines, Comparisons, Glossary | Acne + sensitive skin, AHA vs BHA | Planned | Newsletter 500 subs target
Month 6 | September 2026 | 7 | Ingredient Science, Comparisons, Conditions | Colloidal oatmeal, menopause skin, budget guide | Planned | $1,000/mo run rate
TOP PRIORITIES — TECHNICAL & SEO
# | Task | Category | Priority | Effort | Impact | Status | Notes
1 | Add schema markup (Article + BreadcrumbList) to all pages | SEO | High | Medium | High | Pending | Fixes Ahrefs structured data warnings
2 | Fix 4x 404 broken internal links | Technical | High | Low | High | Pending | Identified in Ahrefs crawl
3 | Add meta descriptions to 5 pages missing them | SEO | High | Low | High | Pending | homepage, about, shop, newsletter, contact
4 | Add Open Graph tags to all pages | SEO | Medium | Medium | Medium | Pending | Required for social sharing previews
5 | Shorten 11 over-length meta descriptions | SEO | Medium | Low | Medium | Pending | Max 155 chars
6 | Add all new pages to sitemap.xml + submit IndexNow | SEO | High | Low | High | Done | Month 1 articles added — submit to IndexNow
7 | Full security audit (CSP, HTTPS, form validation) | Security | High | Medium | High | Pending | Check headers via securityheaders.com
8 | Wire affiliate links (Amazon Associates) | Revenue | High | Medium | High | Pending | 6 review pages + buying guides
9 | Build About + Editorial Policy pages (E-E-A-T) | SEO/Trust | High | Medium | High | Pending | Critical for YMYL ranking
10 | Connect newsletter form to email provider | Growth | Medium | Medium | High | Pending | Recommend ConvertKit or Beehiiv

## Site Inventory
BioSkinRepair — Full Page Inventory
URL | Page Title | Category | Type | Status | Publish Date | Meta Desc? | Schema? | OG Tags? | Ahrefs Issues
bioskinrepair.com/ | BioSkinRepair — Home | Hub | Homepage | Live | 2026-03-27 | Missing | Missing | Missing | Meta desc, OG tags
bioskinrepair.com/skin-barrier-101 | Skin Barrier 101 — Complete Guide | Hub | Pillar Article | Live | 2026-03-27 | Yes | Missing | Missing | Schema, OG tags
bioskinrepair.com/ingredients | Skincare Ingredients Guide | Hub | Hub Page | Live | 2026-03-27 | Yes | Missing | Missing | Schema, OG tags
bioskinrepair.com/reviews | Skincare Product Reviews | Hub | Hub Page | Live | 2026-03-27 | Yes | Missing | Missing | Schema, OG tags
bioskinrepair.com/skin-conditions | Skin Conditions & Barrier Damage | Hub | Hub Page | Live | 2026-03-27 | Yes | Missing | Missing | Schema, OG tags
bioskinrepair.com/blog | BioSkinRepair Blog | Hub | Hub Page | Live | 2026-03-27 | Yes | Missing | Missing | Schema, OG tags
bioskinrepair.com/routines | Barrier Repair Routines | Hub | Hub Page | Live | 2026-03-27 | Yes | Missing | Missing | Schema, OG tags
bioskinrepair.com/guides | Skincare Guides | Hub | Hub Page | Live | 2026-03-27 | Yes | Missing | Missing | Schema, OG tags
bioskinrepair.com/shop | Shop — Barrier Repair Products | Commerce | Shop Page | Live | 2026-03-27 | Missing | Missing | Missing | Meta desc, OG tags
bioskinrepair.com/ceramides | Ceramides in Skincare — Complete Guide | Ingredient | Deep-Dive | Live | 2026-03-27 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/niacinamide-skin-barrier | Niacinamide for Skin Barrier | Ingredient | Deep-Dive | Live | 2026-03-28 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/tewl | What Is TEWL? | Glossary | Glossary Entry | Live | 2026-03-28 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/humectant | What Is a Humectant? | Glossary | Glossary Entry | Live | 2026-03-28 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/emollient | What Is an Emollient? | Glossary | Glossary Entry | Live | 2026-03-28 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/eczema | Eczema & Skin Barrier Damage | Skin Condition | Condition Guide | Live | 2026-03-27 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/rosacea | Rosacea & Sensitive Skin Barrier | Skin Condition | Condition Guide | Live | 2026-03-27 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/over-exfoliation | Over-Exfoliation Recovery | Skin Condition | Condition Guide | Live | 2026-03-27 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/sensitive-skin | Sensitive Skin Barrier Guide | Skin Condition | Condition Guide | Live | 2026-03-27 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/how-long-skin-barrier-repair | How Long Does Skin Barrier Repair Take? | Barrier Recovery | Article | Live | 2026-03-28 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/signs-skin-barrier-is-healing | Signs Your Skin Barrier Is Healing | Barrier Recovery | Article | Live | 2026-03-28 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/cerave-vs-cetaphil | CeraVe vs Cetaphil | Comparison | Versus Page | Live | 2026-03-28 | Yes | Missing | Missing | Schema markup
bioskinrepair.com/cerave-moisturizing-cream-review | CeraVe Moisturizing Cream Review | Review | Product Review | Live | 2026-03-27 | Yes | Missing | Missing | Review schema
bioskinrepair.com/eltamd-uv-clear-review | EltaMD UV Clear Review | Review | Product Review | Live | 2026-03-27 | Yes | Missing | Missing | Review schema
bioskinrepair.com/la-roche-posay-cicaplast-review | La Roche-Posay Cicaplast Review | Review | Product Review | Live | 2026-03-27 | Yes | Missing | Missing | Review schema
bioskinrepair.com/paulas-choice-barrier-repair-review | Paula's Choice Barrier Repair Review | Review | Product Review | Live | 2026-03-27 | Yes | Missing | Missing | Review schema
bioskinrepair.com/the-ordinary-natural-moisturizing-review | The Ordinary NMF Review | Review | Product Review | Live | 2026-03-27 | Yes | Missing | Missing | Review schema
bioskinrepair.com/vanicream-gentle-cleanser-review | Vanicream Gentle Cleanser Review | Review | Product Review | Live | 2026-03-27 | Yes | Missing | Missing | Review schema
bioskinrepair.com/about | About BioSkinRepair | Company | About Page | Live | 2026-03-27 | Missing | Missing | Missing | Meta desc, OG, E-E-A-T
bioskinrepair.com/newsletter | Free Barrier Repair Guide | Company | Lead Capture | Live | 2026-03-27 | Missing | Missing | Missing | Meta desc, OG tags
bioskinrepair.com/contact | Contact BioSkinRepair | Company | Contact Page | Live | 2026-03-27 | Missing | Missing | Missing | OG tags
bioskinrepair.com/privacy-policy | Privacy Policy | Legal | Legal Page | Live | 2026-03-27 | Yes | N/A | N/A
bioskinrepair.com/terms | Terms of Use | Legal | Legal Page | Live | 2026-03-27 | Yes | N/A | N/A
SUMMARY
Total pages live:
Missing meta descriptions:
Missing schema:

## Content Calendar
BioSkinRepair — 6-Month Content Calendar (April – September 2026)
Month | Period | Week | URL Slug | Title | Category | Target Keyword | Pub. Date | Word Count | Status | Internal Links To
0 | Pre-launch | W0 | /ceramides | Ceramides in Skincare | Ingredient | ceramides skincare | 2026-03-27 | 2800 | Live | skin-barrier-101, eczema
0 | Pre-launch | W0 | /eczema | Eczema & Skin Barrier | Skin Condition | eczema skin barrier | 2026-03-27 | 2400 | Live | ceramides, rosacea, over-exfoliation
0 | Pre-launch | W0 | /rosacea | Rosacea & Sensitive Skin | Skin Condition | rosacea skin barrier | 2026-03-27 | 2200 | Live | ceramides, sensitive-skin
0 | Pre-launch | W0 | /over-exfoliation | Over-Exfoliation Recovery | Skin Condition | over exfoliation recovery | 2026-03-27 | 2300 | Live | routines, ceramides, tewl
0 | Pre-launch | W0 | /sensitive-skin | Sensitive Skin Barrier Guide | Skin Condition | sensitive skin routine | 2026-03-27 | 2100 | Live | eczema, rosacea, ceramides
0 | Pre-launch | W0 | /cerave-moisturizing-cream-review | CeraVe Moisturizing Cream Review | Review | cerave moisturizing cream review | 2026-03-27 | 1800 | Live | ceramides, eczema
0 | Pre-launch | W0 | /eltamd-uv-clear-review | EltaMD UV Clear Review | Review | eltamd uv clear review | 2026-03-27 | 1800 | Live | sensitive-skin, rosacea
0 | Pre-launch | W0 | /la-roche-posay-cicaplast-review | La Roche-Posay Cicaplast Review | Review | la roche posay cicaplast review | 2026-03-27 | 1800 | Live | eczema, ceramides
0 | Pre-launch | W0 | /paulas-choice-barrier-repair-review | Paula's Choice Barrier Repair Review | Review | paulas choice barrier repair | 2026-03-27 | 1800 | Live | ceramides, over-exfoliation
0 | Pre-launch | W0 | /the-ordinary-natural-moisturizing-review | The Ordinary NMF Review | Review | the ordinary natural moisturizing | 2026-03-27 | 1800 | Live | humectant, tewl
0 | Pre-launch | W0 | /vanicream-gentle-cleanser-review | Vanicream Gentle Cleanser Review | Review | vanicream gentle cleanser review | 2026-03-27 | 1600 | Live | sensitive-skin, eczema
1 | April 2026 | W1 | /how-long-skin-barrier-repair | How Long Does Skin Barrier Repair Take? | Barrier Recovery | how long skin barrier repair | 2026-03-28 | 2600 | Live | tewl, ceramides, routines
1 | April 2026 | W1 | /signs-skin-barrier-is-healing | Signs Your Skin Barrier Is Healing | Barrier Recovery | signs skin barrier healing | 2026-03-28 | 2400 | Live | how-long-skin-barrier-repair, tewl
1 | April 2026 | W2 | /cerave-vs-cetaphil | CeraVe vs Cetaphil | Comparison | cerave vs cetaphil | 2026-03-28 | 2200 | Live | ceramides, cerave-moisturizing-cream-review
1 | April 2026 | W2 | /niacinamide-skin-barrier | Niacinamide for Skin Barrier | Ingredient | niacinamide skin barrier | 2026-03-28 | 2500 | Live | ceramides, rosacea
1 | April 2026 | W3 | /tewl | What Is TEWL? | Glossary | transepidermal water loss | 2026-03-28 | 1600 | Live | how-long-skin-barrier-repair, ceramides
1 | April 2026 | W3 | /humectant | What Is a Humectant? | Glossary | humectant definition skincare | 2026-03-28 | 1700 | Live | emollient, ceramides
1 | April 2026 | W4 | /emollient | What Is an Emollient? | Glossary | emollient skincare definition | 2026-03-28 | 1700 | Live | humectant, ceramides, routines
2 | May 2026 | W1 | /hyaluronic-acid | Hyaluronic Acid for Skin Barrier | Ingredient | hyaluronic acid benefits skin | 2026-05-01 | 2500 | Planned | humectant, tewl, niacinamide-skin-barrier
2 | May 2026 | W1 | /perioral-dermatitis | Perioral Dermatitis Guide | Skin Condition | perioral dermatitis | 2026-05-05 | 2400 | Planned | sensitive-skin, rosacea, routines
2 | May 2026 | W2 | /fungal-acne | Fungal Acne Routine | Skin Condition | fungal acne skincare routine | 2026-05-08 | 2300 | Planned | sensitive-skin, ingredients
2 | May 2026 | W2 | /mineral-vs-chemical-sunscreen-sensitive | Mineral vs Chemical Sunscreen | Comparison | mineral vs chemical sunscreen | 2026-05-12 | 2200 | Planned | sensitive-skin, rosacea
2 | May 2026 | W3 | /minimalist-skincare-routine | Minimalist Skincare Routine | Routine | minimalist skincare routine | 2026-05-15 | 2400 | Planned | routines, ceramides, humectant
2 | May 2026 | W3 | /best-ceramide-moisturizer | Best Ceramide Moisturizer (Buying Guide) | Buying Guide | best ceramide moisturizer | 2026-05-19 | 2800 | Planned | ceramides, cerave-moisturizing-cream-review
2 | May 2026 | W4 | /occlusive | What Is an Occlusive? | Glossary | occlusive skincare definition | 2026-05-22 | 1600 | Planned | humectant, emollient, ceramides
3 | June 2026 | W1 | /am-vs-pm-skincare-routine | AM vs PM Skincare Routine | Routine | AM PM skincare routine order | 2026-06-01 | 2400 | Planned | routines, ceramides, niacinamide-skin-barrier
3 | June 2026 | W1 | /how-to-reintroduce-retinol | How to Reintroduce Retinol After Barrier Damage | Routine | how to reintroduce retinol | 2026-06-05 | 2600 | Planned | routines, how-long-skin-barrier-repair
3 | June 2026 | W2 | /contact-dermatitis-vs-eczema | Contact Dermatitis vs Eczema | Skin Condition | contact dermatitis vs eczema | 2026-06-09 | 2200 | Planned | eczema, sensitive-skin
3 | June 2026 | W2 | /retinol-vs-retinoid-vs-tretinoin | Retinol vs Retinoid vs Tretinoin | Comparison | retinol vs retinoid vs tretinoin | 2026-06-12 | 2400 | Planned | how-to-reintroduce-retinol, over-exfoliation
3 | June 2026 | W3 | /best-cleanser-damaged-skin-barrier | Best Cleanser for Damaged Skin Barrier | Buying Guide | best cleanser damaged skin barrier | 2026-06-16 | 2800 | Planned | routines, ceramides, over-exfoliation
3 | June 2026 | W3 | /bioderma-sensibio-review | Bioderma Sensibio Review | Review | bioderma sensibio review | 2026-06-19 | 1800 | Planned | sensitive-skin, rosacea
3 | June 2026 | W4 | /sensitized-skin | What Is Sensitized Skin? | Glossary | sensitized skin definition | 2026-06-22 | 1600 | Planned | sensitive-skin, eczema
4 | July 2026 | W1 | /peptides | Peptides in Skincare | Ingredient | peptides in skincare benefits | 2026-07-01 | 2500 | Planned | ceramides, niacinamide-skin-barrier
4 | July 2026 | W1 | /centella-asiatica | Centella Asiatica / Cica Benefits | Ingredient | centella asiatica benefits | 2026-07-05 | 2400 | Planned | ceramides, eczema, rosacea
4 | July 2026 | W2 | /dry-vs-dehydrated-skin | Dry vs Dehydrated Skin | Skin Condition | dry vs dehydrated skin | 2026-07-08 | 2200 | Planned | humectant, tewl, routines
4 | July 2026 | W2 | /aveeno-vs-cerave-eczema | Aveeno vs CeraVe for Eczema | Comparison | aveeno vs cerave eczema | 2026-07-12 | 2200 | Planned | eczema, ceramides, cerave-moisturizing-cream-review
4 | July 2026 | W3 | /best-sunscreen-sensitive-skin | Best Sunscreen for Sensitive Skin | Buying Guide | best sunscreen sensitive skin | 2026-07-16 | 2800 | Planned | sensitive-skin, eltamd-uv-clear-review, rosacea
4 | July 2026 | W3 | /avene-cicalfate-review | Avène Cicalfate+ Review | Review | avene cicalfate review | 2026-07-19 | 1800 | Planned | eczema, ceramides, rosacea
4 | July 2026 | W4 | /skin-microbiome | What Is the Skin Microbiome? | Glossary | skin microbiome definition | 2026-07-22 | 1700 | Planned | eczema, ceramides
5 | August 2026 | W1 | /skin-barrier-vs-moisture-barrier | Skin Barrier vs Moisture Barrier | Barrier Recovery | skin barrier vs moisture barrier | 2026-08-01 | 2200 | Planned | tewl, skin-barrier-101, ceramides
5 | August 2026 | W1 | /acne-sensitive-skin-routine | Acne + Sensitive Skin Routine | Routine | acne sensitive skin routine | 2026-08-05 | 2600 | Planned | niacinamide-skin-barrier, routines
5 | August 2026 | W2 | /seborrheic-dermatitis | Seborrheic Dermatitis Guide | Skin Condition | seborrheic dermatitis skincare | 2026-08-08 | 2400 | Planned | sensitive-skin, skin-microbiome
5 | August 2026 | W2 | /how-to-layer-skincare | How to Layer Skincare Products | Routine | how to layer skincare | 2026-08-12 | 2400 | Planned | routines, niacinamide-skin-barrier, humectant
5 | August 2026 | W3 | /aha-vs-bha-sensitive-skin | AHA vs BHA for Sensitive Skin | Comparison | AHA vs BHA sensitive skin | 2026-08-16 | 2400 | Planned | over-exfoliation, how-to-reintroduce-retinol
5 | August 2026 | W3 | /best-moisturizer-eczema | Best Moisturizer for Eczema | Buying Guide | best moisturizer eczema | 2026-08-19 | 2800 | Planned | eczema, ceramides, cerave-moisturizing-cream-review
5 | August 2026 | W4 | /skincare-ph | Skincare pH — Why It Matters | Glossary | skincare pH balance | 2026-08-22 | 1700 | Planned | over-exfoliation, emollient
6 | September 2026 | W1 | /colloidal-oatmeal | Colloidal Oatmeal for Skin Barrier | Ingredient | colloidal oatmeal benefits | 2026-09-01 | 2400 | Planned | eczema, ceramides, humectant
6 | September 2026 | W1 | /linoleic-acid | Linoleic Acid in Skincare | Ingredient | linoleic acid skincare | 2026-09-05 | 2300 | Planned | ceramides, emollient, tewl
6 | September 2026 | W2 | /menopause-skin-barrier | Menopause & Skin Barrier Changes | Skin Condition | menopause skin barrier | 2026-09-08 | 2400 | Planned | tewl, ceramides, routines
6 | September 2026 | W2 | /niacinamide-vs-hyaluronic-acid | Niacinamide vs Hyaluronic Acid | Comparison | niacinamide vs hyaluronic acid | 2026-09-12 | 2200 | Planned | niacinamide-skin-barrier, hyaluronic-acid
6 | September 2026 | W3 | /affordable-barrier-repair-skincare | Best Budget Barrier Repair Skincare | Buying Guide | affordable barrier repair skincare | 2026-09-16 | 2800 | Planned | ceramides, cerave-moisturizing-cream-review
6 | September 2026 | W3 | /cerave-vs-neutrogena-hydro-boost | CeraVe vs Neutrogena Hydro Boost | Comparison | cerave vs neutrogena hydro boost | 2026-09-19 | 2200 | Planned | ceramides, cerave-moisturizing-cream-review, humectant
6 | September 2026 | W4 | /skin-purging-vs-reaction | Skin Purging vs Reaction | Skin Condition | skin purging vs reaction | 2026-09-22 | 2000 | Planned | over-exfoliation, how-to-reintroduce-retinol
MONTH COLOUR LEGEND
Month 0 | Month 0 — Pre-launch | Month 1 | Month 1 — April | Month 2 | Month 2 — May | Month 3 | Month 3 — June | Month 4 | Month 4 — July | Month 5 | Month 5 — August | Month 6 | Month 6 — September
TOTALS
Total articles planned:
Live:
Planned:

## Keyword Strategy
BioSkinRepair — SEO Keyword Strategy
Target Keyword | URL | Category | Monthly Volume (Est.) | KD (Est.) | Intent | Priority | Current Rank | Target Rank | Notes
skin barrier repair | /skin-barrier-101 | Pillar | 40,500 | 55 | Informational | High | — | Top 10 | Core pillar page
how to repair skin barrier | /skin-barrier-101 | Pillar | 22,200 | 52 | Informational | High | — | Top 10 | Alt intent for pillar
damaged skin barrier | /skin-barrier-101 | Pillar | 18,100 | 48 | Informational | High | — | Top 10 | Captures distress query
ceramides in skincare | /ceramides | Ingredient | 12,100 | 44 | Informational | High | — | Top 5 | Deep-dive page
cerave vs cetaphil | /cerave-vs-cetaphil | Comparison | 27,100 | 38 | Commercial | High | — | Top 5 | High CTR comparison query
how long skin barrier repair | /how-long-skin-barrier-repair | Recovery | 8,100 | 32 | Informational | High | — | Top 5 | Long-tail, low KD
niacinamide skin barrier | /niacinamide-skin-barrier | Ingredient | 6,600 | 38 | Informational | High | — | Top 5 | Growing ingredient interest
signs skin barrier healing | /signs-skin-barrier-is-healing | Recovery | 3,600 | 28 | Informational | High | — | Top 3 | Very winnable long-tail
eczema skin barrier | /eczema | Condition | 14,800 | 50 | Informational | High | — | Top 10 | Condition hub
rosacea skin barrier | /rosacea | Condition | 8,100 | 46 | Informational | High | — | Top 10 | Condition hub
over exfoliation recovery | /over-exfoliation | Condition | 5,400 | 35 | Informational | High | — | Top 5 | Intent match very strong
sensitive skin routine | /sensitive-skin | Condition | 18,100 | 45 | Informational | High | — | Top 10 | High volume condition page
cerave moisturizing cream review | /cerave-moisturizing-cream-review | Review | 14,800 | 40 | Commercial | High | — | Top 5 | High affiliate value
eltamd uv clear review | /eltamd-uv-clear-review | Review | 9,900 | 38 | Commercial | High | — | Top 5 | High affiliate value
transepidermal water loss | /tewl | Glossary | 1,900 | 30 | Informational | Medium | — | Top 3 | Clinical term, easy to rank
what is a humectant | /humectant | Glossary | 3,600 | 28 | Informational | Medium | — | Top 3 | Low competition
what is an emollient | /emollient | Glossary | 2,900 | 27 | Informational | Medium | — | Top 3 | Low competition
hyaluronic acid dry skin | /hyaluronic-acid | Ingredient | 22,200 | 46 | Informational | Medium | — | Top 10 | Month 2
fungal acne routine | /fungal-acne | Condition | 9,900 | 36 | Informational | Medium | — | Top 5 | Month 2 — rising trend
best ceramide moisturizer | /best-ceramide-moisturizer | Buying | 14,800 | 42 | Commercial | Medium | — | Top 5 | Month 2 buying guide
mineral vs chemical sunscreen | /mineral-vs-chemical-sunscreen-sensitive | Comparison | 18,100 | 44 | Commercial | Medium | — | Top 10 | Month 2
retinol vs retinoid vs tretinoin | /retinol-vs-retinoid-vs-tretinoin | Comparison | 12,100 | 50 | Informational | Medium | — | Top 10 | Month 3
best cleanser sensitive skin | /best-cleanser-damaged-skin-barrier | Buying | 18,100 | 46 | Commercial | Medium | — | Top 10 | Month 3 buying guide
peptides in skincare | /peptides | Ingredient | 12,100 | 44 | Informational | Medium | — | Top 10 | Month 4
centella asiatica skincare | /centella-asiatica | Ingredient | 8,100 | 38 | Informational | Medium | — | Top 5 | Month 4
aveeno vs cerave eczema | /aveeno-vs-cerave-eczema | Comparison | 5,400 | 35 | Commercial | Medium | — | Top 5 | Month 4
best sunscreen sensitive skin | /best-sunscreen-sensitive-skin | Buying | 22,200 | 48 | Commercial | Medium | — | Top 10 | Month 4
minimalist skincare routine | /minimalist-skincare-routine | Routine | 8,100 | 38 | Informational | Medium | — | Top 5 | Month 2
how to layer skincare products | /how-to-layer-skincare | Routine | 14,800 | 42 | Informational | Medium | — | Top 10 | Month 5
AHA vs BHA sensitive skin | /aha-vs-bha-sensitive-skin | Comparison | 6,600 | 40 | Informational | Medium | — | Top 5 | Month 5
best moisturizer for eczema | /best-moisturizer-eczema | Buying | 18,100 | 46 | Commercial | Medium | — | Top 10 | Month 5
colloidal oatmeal benefits | /colloidal-oatmeal | Ingredient | 5,400 | 34 | Informational | Low | — | Top 5 | Month 6
skin purging vs reaction | /skin-purging-vs-reaction | Condition | 8,100 | 36 | Informational | Low | — | Top 5 | Month 6
niacinamide vs hyaluronic acid | /niacinamide-vs-hyaluronic-acid | Comparison | 12,100 | 40 | Informational | Low | — | Top 5 | Month 6

## Technical Backlog
BioSkinRepair — Technical & SEO Backlog
# | Task | Category | Priority | Effort | Impact | Status | Target Sprint | Notes
1 | Fix 4x broken internal links (404) | SEO — Error | High | Low | High | Pending | Sprint 1 | Identify pages, update href targets
2 | Add Article schema to all article/review pages (30+ pages) | SEO — Schema | High | Medium | High | Pending | Sprint 1 | JSON-LD in <head>. Fixes Ahrefs structured data warning
3 | Add BreadcrumbList schema to all pages | SEO — Schema | High | Medium | High | Pending | Sprint 1 | Pair with visible breadcrumb nav already in pages
4 | Add Product + Review schema to 6 review pages | SEO — Schema | High | Medium | High | Pending | Sprint 1 | Required for Google rich results on review pages
5 | Add meta descriptions to: home, about, shop, newsletter, contact | SEO — Meta | High | Low | High | Pending | Sprint 1 | Max 155 chars. 5 pages flagged by Ahrefs
6 | Shorten 11 meta descriptions >155 chars | SEO — Meta | Medium | Low | Medium | Pending | Sprint 1 | Trim without losing target keyword
7 | Shorten 10 page titles >60 chars | SEO — Meta | Medium | Low | Medium | Pending | Sprint 1 | Keep keyword near front
8 | Add Open Graph tags (og:title, og:description, og:image) to all pages | SEO — OG | Medium | Medium | Medium | Pending | Sprint 1 | Required for social sharing cards
9 | Add Twitter Card meta tags | SEO — OG | Low | Low | Low | Pending | Sprint 2 | twitter:card, twitter:title, twitter:image
10 | Investigate 3x 3XX redirect chains | SEO — Technical | Medium | Low | Medium | Pending | Sprint 1 | Check vercel.json redirects
11 | Submit all new pages via IndexNow | SEO — Indexing | High | Low | High | Pending | Sprint 1 | Requires IndexNow API key setup
12 | Create robots.txt | SEO — Technical | Medium | Low | Medium | Pending | Sprint 1 | Currently missing — Vercel may serve default
13 | Add canonical tags to all pages | SEO — Technical | Medium | Medium | Medium | Pending | Sprint 2 | Prevent duplicate content issues
14 | Security headers audit (CSP, X-Frame, HSTS, etc.) | Security | High | Low | High | Pending | Sprint 1 | Run securityheaders.com scan
15 | Add Content-Security-Policy header via vercel.json | Security | High | Low | High | Pending | Sprint 1 | Allow only trusted scripts
16 | Add X-Frame-Options: DENY header | Security | High | Low | Medium | Pending | Sprint 1 | Prevent clickjacking
17 | Add X-Content-Type-Options: nosniff header | Security | Medium | Low | Medium | Pending | Sprint 1 | Prevent MIME sniffing
18 | Validate all newsletter form inputs (client + server-side) | Security | Medium | Low | Medium | Pending | Sprint 2 | No backend yet — ensure form goes to trusted provider
19 | Review affiliate link rel=nofollow + noopener attributes | Security | Medium | Low | Low | Pending | Sprint 2 | All external buy links should have rel='nofollow noopener'
20 | Register for Amazon Associates affiliate program | Revenue | High | Low | High | Pending | Sprint 1 | US + UK + DE if targeting international traffic
21 | Replace all # buy links with Amazon affiliate URLs | Revenue | High | Medium | High | Pending | Sprint 1 | 6 review pages + buying guides — highest revenue impact
22 | Connect newsletter form to email provider (ConvertKit/Beehiiv) | Growth | High | Medium | High | Pending | Sprint 1 | Currently form submits nowhere — losing subscribers
23 | Build About page with author bio + credentials (E-E-A-T) | Trust/SEO | High | Medium | High | Pending | Sprint 1 | Critical for YMYL niche — Google requires expertise signals
24 | Build Editorial Policy / Review Methodology page | Trust/SEO | High | Medium | High | Pending | Sprint 2 | Required for review schema and reader trust
25 | Set up Google Search Console + submit sitemap | SEO — Indexing | High | Low | High | Pending | Sprint 1 | Essential for monitoring rankings and indexing issues
26 | Set up Google Analytics 4 | Analytics | High | Low | High | Pending | Sprint 1 | Track organic traffic, pages per session, email conversion
27 | Add FAQ schema to top 10 article pages | SEO — Schema | Medium | Medium | Medium | Pending | Sprint 2 | Each article has natural FAQ content
28 | Add HowTo schema to routine pages | SEO — Schema | Low | Low | Medium | Pending | Sprint 3 | routines.html + future routine articles
29 | Add site search functionality | UX | Low | High | Medium | Pending | Sprint 4 | Pagefind.app — static site search, free, works on Vercel
30 | Add reading progress indicator to long articles | UX | Low | Low | Low | Pending | Sprint 4 | Lightweight JS scroll progress bar

## Monetization
BioSkinRepair — Monetization Roadmap
REVENUE STREAMS
Stream | Platform | Commission | Activation | Monthly Target (6mo) | Status | Notes
Amazon Associates | Amazon US/UK | 3–10% | Register + replace # links | $300 | Pending | Primary revenue driver. Priority: review pages + buying guides
LTK / RewardStyle | LTK | 5–20% | Apply (influencer threshold) | $50 | Pending | Higher commissions, better for skincare brands
ShareASale — brands | ShareASale | 8–15% | Apply per brand | $100 | Pending | CeraVe, EltaMD, Paula's Choice have programs
Skimlinks | Skimlinks | Variable | Add JS snippet | $80 | Pending | Auto-converts links — easiest to implement
Display ads (Mediavine) | Mediavine | RPM $15–30 | 50k sessions/month | $0 | Pending | Long-term play — target Month 9+
Newsletter sponsorships | Beehiiv/ConvertKit | Fixed fee | 500 subs minimum | $0 | Pending | 1 sponsored edition/month at 500+ subs
Digital product (PDF guide) | Gumroad | 100% | Build free barrier guide PDF | $50 | Pending | Upsell from free lead magnet
GROWTH MILESTONES
Month | Period | Sessions Target | Pages Live | Email Subs | Revenue Target | Key Milestone | Priority Action
0 | Mar 2026 | < 1,000 | 28 | 0 | $0 | Site launched | Fix technical issues, connect email
1 | Apr 2026 | 1,000+ | 35 | 50 | $0 | First cluster live, Ahrefs fixes | Amazon Associates + GSC setup
2 | May 2026 | 3,000+ | 42 | 150 | $50 | 7 more articles + affiliate links | First affiliate revenue
3 | Jun 2026 | 6,000+ | 49 | 300 | $200 | Buying guides driving clicks | Optimize top affiliate pages
4 | Jul 2026 | 12,000+ | 56 | 500 | $500 | Organic traffic compounding | Pinterest + Instagram launch
5 | Aug 2026 | 20,000+ | 63 | 750 | $800 | Long-tail traffic snowball | Newsletter monetization test
6 | Sep 2026 | 35,000+ | 70 | 1000 | $1,200 | Target Mediavine threshold | SEO audit + content refresh